## Acoustic Ceiling QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification
1 | Ceiling type, grid profile, and acoustic tile model match approved submittals
2 | Tile NRC (Noise Reduction Coefficient), CAC (Ceiling Attenuation Class) ratings match spec
3 | Suspension wires, main tees, cross tees, trims, and hold-down clips reviewed and received
B. Pre-Installation Checks
4 | Mechanical, electrical, and sprinkler rough-ins completed and coordinated with ceiling layout
5 | Perimeter wall angles installed level, continuous, and at correct height
6 | Existing ceiling and services removed (if applicable); substrate conditions verified
C. Grid Suspension Installation
7 | Suspension wires installed to structure and spaced per code (typically 4’ o.c.)
8 | Grid levelled and aligned with laser or string line
9 | Main tees and cross tees clipped securely, square, and tight
10 | Seismic bracing installed where required
D. Tile Installation
11 | Tiles cut cleanly, seated flat in grid, and corners square
12 | Tiles installed tight to grid with no sagging or gaps
13 | Tiles around lights, grilles, sprinklers cut and trimmed neatly
14 | Damaged tiles replaced before handover
E. Coordination & Final Review
15 | Access panels, light fixtures, and HVAC diffusers properly supported
16 | Final height and alignment confirmed with reflected ceiling plan (RCP)
17 | Punch list reviewed and deficiencies corrected
18 | Closeout documents submitted including warranties and acoustical performance data
Code/Standard References:
• NBC, ASTM C635 / C636 – Grid and Suspension Systems
• ASTM E1264 / E84 – Acoustic Tile Performance
• Seismic Code (NBCC 2020, Zone-Specific)
• Manufacturer Specs: Armstrong, CertainTeed, CGC, Rockfon, USG