## Aluminum Windows QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification
1 | Window type (curtain wall, storefront, punched) matches approved shop drawings & architectural intent
2 | Frames, glass, gaskets, fasteners, anchors, and sealants match submittals
3 | Frames inspected for damage, deformation, or finish issues prior to install
B. Pre-Installation Review
4 | Rough openings sized and framed as per tolerance; shims & blocking provided
5 | Air barrier/vapor barrier transitions coordinated at perimeter
6 | Mock-up or first install verified (if required)
C. Frame Installation
7 | Frames installed level, plumb, square, shimmed, and anchored as per engineered detail
8 | Thermal breaks (if required) continuous and undamaged
9 | Head, jamb, sill clips and mullions installed tight with no misalignment
D. Glazing
10 | Glass type (low-E, tempered, laminated, IGU) matches approved glazing schedule
11 | Glazing blocks placed and pressure plates torqued to spec
12 | Setting blocks and edge clearances provided as per system requirement
13 | No scratches, distortions, or blemishes on glass
E. Weatherproofing & Finishes
14 | All perimeter caulking sealed continuously with no voids, cold joints
15 | Transition to WRB/AVB sealed with membrane/tape per detail
16 | Sill pans or drip edges installed as per spec
F. Final QA/QC & Testing
17 | Water and air infiltration tested (ASTM E1105 / E783) if required
18 | Punch list completed; operation, locks, and finishes inspected
19 | Warranty and as-built glazing submittals provided
Code/Standard References:
• NBC Part 5 & 9, CSA A440, ASTM E2112, E1105, E783
• Manufacturer Specs: Kawneer, Alumicor, Oldcastle, YKK, Technal
• Envelope Consultant and Mock-Up Test Requirements
• LEED / NECB / Passive House Certification Goals