## Architectural Woodwork QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification
1 | Wood species, veneers, and finishes as per approved shop drawings and submittals
2 | Hardware (hinges, pulls, glides) matches schedule and samples
3 | Moisture content of wood within acceptable range (6–10%)
4 | All materials stored in climate-controlled, dry environment
B. Millwork & Cabinetry Installation
5 | Cabinets leveled, shimmed, and secured to framing/substrate
6 | Cabinet joints tight and even; face frames flush
7 | Wall panels and trim align with control lines and are plumb and level
8 | Wood blocking in walls confirmed prior to installation of shelving/mirrors
9 | Coordination with appliance contractor completed and clearances verified prior to millwork start
10 | Gaps between millwork and adjacent surfaces caulked or finished per spec
11 | Exposed fasteners minimized and placed neatly or concealed
C. Doors, Trim & Baseboards
12 | Trim and casing cut cleanly, aligned properly at corners and joints
13 | Baseboards installed with tight joints and straight alignments
14 | Window stools, aprons, and sills installed square and flush
15 | Wood doors checked for swing, clearance, and consistent margins
D. Finish Review
16 | Sanding, staining, or sealing completed with uniform appearance
17 | No tool marks, dents, glue stains, or paint drips visible
18 | All surfaces clean, undamaged, and protected until turnover
19 | QA/QC sign-off and client walk-through complete
Code/Standard References:
• AWI (Architectural Woodwork Standards) – Current Edition
• NBC Part 9 – Finishing Materials and Trim Requirements
• LEED/Environmental Requirements (if applicable)
• Project Shop Drawings and Finish Schedule