## Asphalt Paving QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittals & Mix Design Review
1 | Approved paving drawings and pavement design (thickness, lifts, materials) reviewed
2 | Asphalt mix design (job-mix formula, JMF) approved by consultant or city
3 | Weather conditions checked: ambient >5°C, surface dry, and no rain forecasted
B. Subgrade and Base Preparation
4 | Subgrade compacted and tested for density and moisture content
5 | Granular base (GBC or equivalent) placed in lifts and compacted to 100% standard Proctor
6 | Proof rolling completed and approved by consultant prior to asphalt placement
C. Asphalt Placement
7 | Paver preheated and screed adjusted for thickness and slope
8 | Tack coat applied evenly to cold joint or milled surface
9 | Asphalt temperature upon delivery recorded (typically >120°C for hot-mix)
10 | Paving completed in accordance with lift thickness (e.g., 50 mm base, 40 mm surface)
D. Compaction and Testing
11 | Steel drum and pneumatic rollers used within temperature window
12 | Joint compaction and overlaps inspected (cold joints reheated if needed)
13 | Core or nuclear density tests taken and meet compaction spec (typically >92% of max density)
E. Surface and Closeout
14 | Final grade and cross slope confirmed with straight edge and/or level
15 | Surface finish smooth, with no tearing, segregation, or roller marks
16 | Traffic allowed only after full cooling or as specified in project documents
Code/Standard References:
• CSA A23.2, A3000, ASTM D6925, D2041, D2950
• Alberta Transportation Specs, Municipal Road Standards, HMA Best Practices