## BAS QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittals & System Architecture
1 | Control schematics, network diagrams, sequence of operations reviewed and approved by engineer
2 | BAS panel locations coordinated with electrical rooms/mechanical areas and labeled per drawings
3 | Network protocol confirmed (BACnet/IP, MSTP, Modbus, LonWorks, KNX, etc.) and devices properly mapped
B. Panel Installation & Wiring
4 | BAS panels mounted level, accessible, with nameplates, documentation pockets, and lockable doors
5 | All I/O points wired per schematics, tagged, terminated, and free of interference
6 | Shielded cabling, grounding, conduit penetrations sealed, and low-voltage segregation maintained
C. Field Device Installation
7 | Sensors (temperature, humidity, CO2, occupancy) installed per schedule and calibrated
8 | Damper actuators, valve actuators, and flow meters installed, tested for stroke and feedback
9 | Fire alarm and life safety interlocks connected and labeled
D. Programming, Graphics, and Control Logic
10 | Control programs uploaded, verified per sequence, and override protection enabled
11 | User interface (graphics) reviewed for navigation, points labeling, and trend logs
12 | Alarms configured for priority, email/text alerts, and event triggers
E. Commissioning & Handover
13 | Full point-to-point test completed (input/output validation) with signed off matrix
14 | Trending and logging confirmed for energy usage, setpoints, and occupancy behavior
15 | Operator training conducted and login credentials handed over securely
16 | As-built control drawings, network diagram, backups, and user manuals submitted
Code/Standard References:
• ASHRAE Guideline 13, BACnet Standard 135, ANSI/ASHRAE 135.1, CSA C22.1
• LEED EA Credit: Enhanced Commissioning
• Manufacturer Specs: Johnson Controls, Honeywell, Siemens, Schneider, Delta Controls, Tridium Niagara