## Boiler QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittals & Design Review
1 | Boiler type, input/output capacity, and efficiency rating match mechanical schedule
2 | Shop drawings approved: piping, venting, wiring, flue route, expansion tanks, and pump layout
3 | Boiler code compliance verified: CSA B149, ASME Section IV, local gas codes
B. Delivery & Installation
4 | Boiler delivered with CSA/ASME rating plates, installation manual, startup forms
5 | Unit installed level, anchored, and isolated from structure
6 | Primary/secondary piping connected with isolation, check, purge, balancing valves
7 | Expansion tank, pressure relief valve, air separator, and drain valve installed as per design
8 | Condensate drain (if condensing) installed with neutralizer and proper slope
C. Electrical & Controls
9 | Boiler panel wired with proper disconnect, fusing, and overload protection
10 | BAS/DDC points connected: status, faults, flow, temperature, runtime
11 | Outdoor reset and internal safeties verified: high limit, LWCO, gas valve lockout
D. Venting & Gas
12 | Combustion air and flue piping installed per manufacturer and local code
13 | Leak check on all gas fittings performed with certified meter
14 | CO monitor in place and vent termination meets clearance and distance standards
E. Testing & Commissioning
15 | Hydronic system flushed, pressure tested, and air purged
16 | Boiler startup and combustion tuning completed by certified technician
17 | Operating temperatures, pressure, and delta-T across loop verified
18 | Manufacturer startup log and warranty registration completed
Code/Standard References:
• ASHRAE 90.1, CSA B149 (Gas Code), NBC Part 6, CSA B51/B52, NECB 2020
• Manufacturer Specs: Viessmann, Lochinvar, NTI, Cleaver-Brooks, Camus, Weil-McLain