## Concrete Curbs & Walks
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittals & Review
1 | IFC drawings, sections, and layout plan reviewed and staked
2 | Concrete mix design (strength, slump, air content) approved by consultant or municipality
3 | Accessibility features (slopes, detectable warning pads) detailed and approved
B. Subgrade and Formwork
4 | Subgrade compacted and proof rolled with no soft spots
5 | Forms installed true to line/grade with proper slope for drainage
6 | Expansion joints, dowels, and keyways placed where required
C. Reinforcement & Embedments
7 | Rebar or mesh installed with correct spacing and chair support
8 | Sleeves/conduits for utilities or light poles installed before pour
D. Concrete Placement and Finish
9 | Concrete placed within time and temperature window (CSA A23.1 compliance)
10 | Slump, air, and temperature tests performed at start of pour
11 | Surface finished per spec (broom, smooth, etc.) with control joints cut or tooled
12 | Curb face and radii troweled smoothly with no honeycombing
E. Curing & Post-Pour
13 | Curing compound applied or wet burlap/plastic used within 30 mins of finish
14 | Barriers or flags in place to prevent damage from foot or vehicle traffic
15 | Final inspection completed for slope, elevation, cracks, and finish
Code/Standard References:
• CSA A23.1 & A23.2, NBC 2020 Part 3.8 (Accessibility)
• City of Calgary / Edmonton Concrete Details, ASTM C143, C231, C1064