## Concrete Placement QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Pre-Placement Verification
1 | Pour sequence and method approved by structural/consultant team
2 | Pre-pour meeting held with relevant trades, foremen, and inspectors
3 | Formwork inspection completed and signed off
4 | Reinforcement and embeds verified prior to placement
5 | Weather conditions checked and recorded
6 | Mix design approved and verified (type, strength, slump, admixtures)
7 | Access routes, pump lines, chutes, and pour equipment inspected
8 | Required inspection team and third-party testing agency present
B. Concrete Delivery and Testing
9 | Delivery ticket checked (batch time, slump, mix type, air, temperature)
10 | Slump, temperature, and air content tests conducted at site
11 | Cylinders/cubes cast for compressive strength testing
12 | Concrete within allowable time limit from batching to placement
C. Placement Activities
13 | Concrete placed as per approved plan and sequence
14 | Concrete not dropped from height > 5 ft without chute/trunk
15 | No cold joints or segregation observed during placement
16 | Consolidation/vibration performed correctly and continuously
17 | Vibrator type, spacing, and technique verified
18 | Concrete uniformly distributed and leveled to required finish elevation
D. Post-Pour Activities
19 | Surface finish per contract requirements (trowel, broom, etc.)
20 | Formwork labeled and scheduled for removal as per curing requirement
21 | Initial curing started immediately using approved methods (covering, water, curing compound)
22 | Final curing arrangements in place (wet cure, membrane, insulation if cold)
23 | All data (temps, test results, pour log) recorded and signed by QA/QC
Code/Standard References:
• CSA A23.1 – Concrete Materials and Methods of Construction
• CSA A23.2 – Methods of Testing Concrete
• ACI 301 / ACI 309 – Specifications for Concrete Construction & Consolidation
• NBC Part 4 – Structural Requirements