## Cooling Tower QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittals & Design Review
1 | Tower type (induced draft, forced draft, open-loop, closed-loop) matches schedule and capacity
2 | Structural supports, access platforms, vibration isolators detailed and reviewed
3 | Piping layout and basin drain details approved and coordinated
B. Delivery & Installation
4 | Equipment delivered with factory inspection certificates, start-up forms, and manuals
5 | Tower base installed level with clearance for service and airflow
6 | Condenser water lines connected with flexible couplings, balancing valve, strainers, chemical injection ports
7 | Vibration isolators and seismic restraints (if required) installed properly
8 | Overflow, drain, and blowdown piping installed with proper backflow prevention
C. Electrical & Controls
9 | Fan motors and control panels connected, fused, and protected
10 | Water level controller installed and tested (float, ultrasonic, or conductivity)
11 | BAS/DDC integrated with status, fan speeds, basin heater, alarm, and trend points
D. Testing & Commissioning
12 | Flow rates balanced and pressure drop verified across tower
13 | Motor rotation and speed control tested; fan vibration within limits
14 | Basin filled and checked for leaks, overflow, and proper drainage
15 | Water treatment system activated and commissioned
16 | Start-up report and warranty registration submitted by manufacturer rep
Code/Standard References:
• ASHRAE 90.1, ASHRAE Guideline 12, NBC 2019, NECB
• CTI STD-201, CSA B52, Local Water Bylaws (Blowdown Limits)
• Manufacturer Specs: Evapco, BAC, Marley, SPX, Delta, Johnson Controls