## EIFS QAQC Checklist
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Pre-Installation Checks
1 | Submittals for system components (insulation, mesh, base coat, finish coat, fasteners) approved
2 | EIFS installer certified by manufacturer
3 | Pre-construction meeting completed with trades, GC, consultant
4 | Mock-up panel approved (if required)
B. Substrate Preparation
5 | Wall substrate (e.g., sheathing) dry, clean, structurally sound
6 | Fasteners flush and no protruding nails, screws, or damage
7 | Control and expansion joint layout verified per drawings
C. Moisture Barrier / WRB
8 | WRB installed continuously with minimum 100 mm laps
9 | All window/door openings wrapped and sealed with waterproof membrane
10 | Sill flashing and pan flashing at rough openings completed before EIFS
11 | Mesh or membrane embedded across sheathing joints (if required by system)
D. Insulation Board Installation
12 | Insulation boards of approved thickness and type
13 | Adhesive applied with full coverage or ribbons as per manufacturer
14 | Boards installed with staggered vertical joints, tight, and level
15 | No gaps >2 mm between boards; foam applied at gaps and tooled
16 | Mechanical fasteners used where required (especially over CMU)
17 | Termination at grade min. 200 mm above finished grade unless otherwise specified
E. Base Coat & Mesh Reinforcement
18 | Reinforcing mesh fully embedded in wet base coat
19 | Mesh overlaps a minimum of 65 mm (2.5”)
20 | Backwrap at terminations (top, bottom, openings) and edges completed
21 | Corner mesh installed at all external corners
22 | Additional high-impact mesh at vulnerable locations (ground level, doors, etc.)
23 | Base coat thickness checked as per spec (typically 1.5–3 mm)
F. Finish Coat Application
24 | Surface cleaned and dry before finish coat application
25 | Finish coat applied uniformly with no visible mesh or patch marks
26 | Finish color and texture matches approved mock-up or sample
27 | Finish coat protected from rain until fully cured
G. Final QA Review & Clean-Up
28 | All terminations sealed and weeps installed at base of wall
29 | Sealant joints between EIFS and dissimilar materials completed
30 | Flashings visible and integrated with water-resistive barrier
31 | QA/QC inspection completed and photos taken prior to scaffolding removal
32 | Manufacturer warranty and install logbook submitted (if required)
Code/Standard References:
• NBC Part 5 & 9 – Moisture Protection & Cladding
• EIMA / ASTM E2568, E2273 – EIFS Components & Drainage Systems
• Manufacturer Guidelines: Dryvit, Sto, Senergy, Parex
• LEED / Energy Code (if continuous insulation required)