## Elevator QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittal Review & Coordination
1 | Elevator type (hydraulic, traction, MRL), capacity, speed, stops match drawings and spec
2 | Shop drawings and layout approved by consultant and coordinated with structural and MEP trades
3 | Cab finish schedule (walls, flooring, handrails, ceiling) matches architectural design intent
4 | Power requirement, shaft ventilation, and lighting coordinated
B. Shaft & Pit Preparation
5 | Shaft dimensions verified against elevator supplier layout
6 | Pit depth, sump pump, and waterproofing installed per manufacturer and local code
7 | Hoist beam, brackets, and embedded steel placed per elevator supplier drawings
8 | Machine room or overhead clearance provided per shop drawings
C. Installation Monitoring
9 | Rails, buffers, hoist cables (if applicable) installed and aligned
10 | Car frame, counterweight, and guide shoes assembled per spec
11 | Cab enclosure installed, finish materials protected until turnover
12 | Doors, operators, and door tracks aligned and function-tested
13 | Fire recall, intercom, emergency lighting, and battery backup installed
D. Final Inspection & Certification
14 | Safety tests completed: load test, overspeed, emergency brake
15 | Inspection passed by provincial/state elevator authority (e.g., TSSA, ASME inspector)
16 | Final cleaning, decals, Braille signage, and safety notices installed
17 | Warranty, logbooks, and operation manual submitted
18 | Handover & owner/operator training confirmed
Code/Standard References:
• ASME A17.1 / CSA B44, ADA / CSA B651, NBC, TSSA (Ontario)
• ISO 4190, Manufacturer Specs: Otis, KONE, ThyssenKrupp, Schindler, Mitsubishi