## Emergency Power QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittals & Design Review
1 | Generator sizing, voltage, phase, and fuel type match electrical schedule and one-line diagram
2 | ATS ratings, number of poles, and location per shop drawings and CSA C282 (or NEC Article 700/701)
3 | Life safety system loads separated and properly labeled
B. Equipment Installation
4 | Generator pad and housing installed per manufacturer spec with seismic anchoring (if required)
5 | Exhaust, intake, and fuel lines routed and tested for leaks
6 | Generator grounding electrode and bonding installed and tested
7 | ATS installed level, wired correctly for both normal and emergency sources
8 | Critical loads wired per fire/life safety codes with no unauthorized loads connected
C. Functional Testing & Startup
9 | Generator pre-start inspection completed: oil, coolant, battery, fuel, alarms
10 | Generator started manually and under automatic transfer
11 | ATS functionality verified: time delay, sensing, transfer, re-transfer
12 | Emergency loads picked up and de-energized without issue during test
13 | Load bank test or connected full-load test conducted and recorded (as required)
14 | Run time verification per spec (e.g., 2 hrs full load or as per CSA/NEC)
D. Closeout & Documentation
15 | As-built single-line, test logs, fuel certification (for diesel), and CSA/UL label on generator submitted
16 | Local AHJ or fire department signoff completed
Code/Standard References:
• CSA C282, NEC Articles 700/701, NFPA 110, UL 2200, NBC Part 3 & 6
• Manufacturer Specs: Generac, Kohler, Cummins, MTU, ASCO, Eaton