## Epoxy Flooring QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification
1 | Epoxy/resinous floor system type (self-leveling, flake, quartz, urethane) matches approved submittals
2 | Coating thickness and system components (primer, base coat, broadcast media, topcoat) confirmed
3 | Material stored per manufacturer guidelines (temperature, humidity, shelf life)
4 | SDS, VOC data, and finish samples submitted and approved
B. Substrate Evaluation & Prep
5 | Substrate dry, clean, free from curing compound, sealers, or laitance
6 | Moisture test (ASTM F2170 or F1869) conducted and passed
7 | Surface prep performed (shot blast, grind, scarify) to meet CSP level per spec (e.g., CSP 3–5)
8 | Repairs to cracks, divots, joints, and edges completed
C. Installation Process
9 | Primer coat applied and allowed proper cure
10 | Base coat applied evenly at specified thickness (in mils or mm)
11 | Aggregate/flakes/quartz broadcast uniformly if system requires
12 | Topcoat applied at specified DFT (dry film thickness) and spread rate
13 | Cove base or vertical upturns installed (if applicable)
D. Final Inspection
14 | Surface texture, color, sheen, and gloss consistent throughout
15 | No pinholes, bubbles, fisheyes, or delamination
16 | Slip resistance tested and meets project criteria (ASTM D2047 / ANSI A137.1)
17 | Coating cure complete before traffic allowed
18 | Closeout documents submitted (maintenance manual, warranty, installer certification)
Code/Standard References:
• ASTM F3010 / F1869 / F2170 / D2047, ACI 515.2, LEED VOC
• Manufacturer Specs: Sika, Tnemec, Stonhard, Dur-A-Flex, Flowcrete, Sherwin-Williams
• Slab prep guide per ICRI CSP standards (Concrete Surface Profile)