## Excavation & Backfill QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Pre-Excavation Preparation
1 | Stamped IFC drawings, geotechnical report, and excavation plan reviewed
2 | Underground utility locates (One Call) completed and visible on site
3 | Traffic, erosion control, and safety barriers installed
B. Excavation Work
4 | Excavation performed to lines, grades, slopes, and benches per IFC drawings
5 | Dewatering systems active if groundwater or rainfall present
6 | Temporary shoring/slope protection installed if required by geotechnical engineer
7 | Excavated material stockpiled, protected, or hauled off site as per reuse criteria
C. Bedding and Pipe Zone
8 | Trench bottom leveled and free of rock or debris
9 | Sand or gravel bedding compacted under and around pipe (as specified)
10 | Proper pipe zone material placed and compacted in lifts to minimum cover depth
D. Backfilling and Compaction
11 | Select backfill placed in uniform lifts (max 150–300 mm) and moisture adjusted
12 | Compaction equipment appropriate for trench size and lift depth
13 | Field density tests performed at required intervals and meet minimum % Proctor
14 | No frozen or organic material used in backfill
E. Closeout & Records
15 | Compaction test reports submitted by third-party testing agency
16 | Excavation log/as-built grades submitted if requested
Code/Standard References:
• ASTM D1557, ASTM D6938, CSA A23.1, OH&S Excavation Guidelines
• Project Geotechnical Report, Alberta Transportation Guidelines (if applicable)