## Excavation & Backfill QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Pre-Excavation Preparation
1 | Stamped IFC drawings, geotechnical report, and excavation plan reviewed
2 | Underground utility locates (One Call) completed and visible on site
3 | Traffic, erosion control, and safety barriers installed
B. Excavation Work
4 | Excavation performed to lines, grades, slopes, and benches per IFC drawings
5 | Dewatering systems active if groundwater or rainfall present
6 | Temporary shoring/slope protection installed if required by geotechnical engineer
7 | Excavated material stockpiled, protected, or hauled off site as per reuse criteria
C. Bedding and Pipe Zone
8 | Trench bottom leveled and free of rock or debris
9 | Sand or gravel bedding compacted under and around pipe (as specified)
10 | Proper pipe zone material placed and compacted in lifts to minimum cover depth
11 | Bedding and pipe zone material approved by consultant or geo report
12 | Gradation or sieve analysis results submitted and confirmed compliant
13 | Crushed gravel, sand, or granular type confirmed per ASTM or CSA specs (e.g., ¾” minus, Type I, Type II)
D. Backfilling and Compaction
14 | Select backfill placed in uniform lifts (max 150–300 mm) and moisture adjusted
15 | Compaction equipment appropriate for trench size and lift depth
16 | Field density tests performed at required intervals and meet minimum % Proctor
17 | No frozen or organic material used in backfill
18 | Import material approvals documented and traceable (trucking tickets, source ID)
19 | Visual inspection for clay clumps, oversized rocks, or moisture content
20 | Lift depths, moisture content, and compaction effort (pass counts) logged per lift
E. Closeout & Records
21 | Compaction test reports submitted by third-party testing agency
22 | Excavation log/as-built grades submitted if requested
Code/Standard References:
• ASTM D1557, ASTM D6938, CSA A23.1, OH&S Excavation Guidelines
• Project Geotechnical Report, Alberta Transportation Guidelines (if applicable)