## Fan Coil QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittals & Design Review
1 | Fan coil type (horizontal, vertical, recessed, exposed) and configuration matches mechanical schedule
2 | Coil type (2-pipe/4-pipe, chilled water, hot water, electric) verified with model and performance data
3 | Shop drawings approved: unit dimensions, connection locations, controls, access clearances
B. Delivery & Installation
4 | Units delivered intact, factory-sealed, with O&M manuals and data plates
5 | Unit installed plumb, level, and securely supported with isolation mounts or hangers
6 | Coil piping connected with unions, isolation valves, balancing valves, and strainers
7 | Drain pans trapped, sloped, insulated, and connected to sanitary drain
8 | Access panels and filters fully accessible per O&M
C. Electrical & Controls
9 | Fan motors wired and confirmed with correct voltage, phasing, overload protection
10 | Thermostat or BAS control wiring connected and labeled
11 | Condensate pump (if applicable) tested and routed properly
D. Commissioning & Final Checks
12 | Unit started and airflow verified in all speeds
13 | Coil flows balanced (flow rate GPM verified), delta-T across coil acceptable
14 | Fan noise and vibration checked
15 | Final cleaning and filter installation completed
16 | Warranty forms and closeout documentation submitted
Code/Standard References:
• ASHRAE 55, 62.1, SMACNA Air Outlets, NBC 2019 Part 6, NECB 2020
• CSA C22.1 (Electrical), CSA B52 (Refrigeration where applicable)
• Manufacturer Specs: Daikin, Carrier, Trane, Magic Aire, Innova, Jaga, Unilux