## Fire Alarm QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittals & Design Review
1 | Fire alarm system design and one-line diagram reviewed and approved
2 | System classification (NFPA 72) and code compliance (local authority) verified
3 | Notification appliances, detection devices, and control panel specifications confirmed
B. Equipment Installation
4 | Fire alarm control panel (FACP) installed in accessible, ventilated location with proper seismic anchorage
5 | Wiring installed per code, securely fastened, and properly tagged
6 | Fire alarm devices (detectors, pull stations, horns, strobes) installed in proper locations as per design
7 | Manual pull stations mounted at proper height, with clear labeling and unobstructed access
8 | Smoke and heat detectors located and installed per NFPA and manufacturer specifications
C. System Integration & Wiring
9 | Interconnection between fire alarm control panel and HVAC, elevators, lighting systems verified
10 | Emergency power supply (UPS or generator) for fire alarm panel confirmed and tested
11 | Circuiting for notification and detection devices confirmed, polarity checked
D. Testing & Commissioning
12 | System tested for all alarm conditions (smoke, heat, manual, supervisory)
13 | Notification devices activated and verified for adequate coverage (audible and visible alarms)
14 | Signal integrity, communication with monitoring station (if applicable) tested
15 | Final alarm test (with fire department coordination, if necessary) completed and signed off
E. Closeout & Documentation
16 | As-built drawings, system schematics, and point-to-point test logs submitted
17 | Operator training completed, with system manual and emergency procedures provided
Code/Standard References:
• NFPA 72, NFPA 101, CSA C22.1 (CEC), UL 864, IBC 2018, NBC 2019
• Manufacturer Specs: Honeywell, Siemens, Bosch, Johnson Controls, Kidde, Hochiki