## Fire Sprinkler QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittal & Regulatory Compliance
1 | Sprinkler system type (wet, dry, pre-action) matches design scope and NFPA classification
2 | Submittals reviewed and stamped by certified engineer (referencing NFPA 13, 25, local AHJ)
3 | Hazard classification confirmed per occupancy (Light, OH-1, OH-2, Special Hazard, Lab) as per HMS & NFPA 13
4 | Hydraulic calculations include 10 PSI safety margin, flow data current and traceable
5 | Drawings include clear hydraulic reference points, compliant to AHJ and site-specific layout
B. Material Delivery & Verification
6 | UL/FM listed sprinkler heads, risers, valves, pressure gauges, tamper switches, and alarms confirmed
7 | System piping verified per spec: Sched 40 black steel, grooved/cut per manufacturer, no torch-cutting
8 | Isolation valves (OS&Y) accessible and clearly tagged with supervision where required
C. Installation Checkpoints
9 | Sprinkler head spacing, elevation, and clearances verified per NFPA 13 and ceiling condition
10 | Pipe hangers and seismic bracing installed per NFPA 13, ANSI/AWWA and manufacturer's instructions
11 | Pressure-reducing valves and relief piping installed and adjusted per location requirements
12 | Air vents and flushing valves installed at system high/low points (for wet/dry systems)
D. Commissioning & Testing
13 | Hydrostatic test: 200 psi for 2 hours successfully passed and documented
14 | Flow switches, tamper switches, pressure alarms triggered correctly
15 | Main drain test completed; pressure drop within acceptable differential
16 | Trip test completed (for dry or pre-action) with full reset and drain documented
17 | Preaction panels tested for initiating circuits and functionality
E. Closeout & Maintenance Setup
18 | System tagged with updated hydraulic demand placards, head lists, and zone maps
19 | Life Safety Records binder provided with inspection logs (initial/annual/monthly per NFC-AE 2019)
20 | Inspection, Testing, and Maintenance forms completed (per CAN/ULC-S536, NFPA 25, Section 21 01 90B)
21 | AHJ and insurance inspections passed, certificates submitted
Code/Standard References:
• NFPA 13, 14, 25, CAN/ULC S524, CAN/ULC S536, NFC-AE 2019, NBC 2019
• Alberta Infrastructure Spec 21 01 90, City of Calgary Responsibilities Guide
• Manufacturer Specs: Viking, Tyco, Reliable, Victaulic, Globe, Watts, Wilkins