## Foundation Waterproofing QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification
1 | Waterproofing membrane (sheet/applied/spray) type and thickness as per approved submittal
2 | Drainage board, protection board, primers, and termination bars match drawings/spec
3 | Materials stored upright, dry, and protected from damage/UV per manufacturer guidelines
B. Substrate Preparation
4 | Concrete cured min. 7 days (for sheet/spray membranes), clean, dry, and free of honeycombs, laitance
5 | Wall tie holes patched; transitions between wall/footing filleted or reinforced
6 | Termination areas marked and accessible
C. Waterproofing Installation
7 | Membrane installed continuous, with shingle overlap at seams (min. 75 mm / 3")
8 | Inside/outside corners reinforced per detail
9 | All penetrations (pipes, rebar dowels, electrical) sealed with boots or compatible detail
10 | Horizontal-to-vertical transition wrapped continuously
D. Drainage & Protection Layers
11 | Drainage board installed without puncturing membrane, overlaps secured
12 | Filter fabric overlaps as per drawing (typically 100 mm)
13 | Termination bar and sealant applied where required
E. Final Inspection
14 | System visually inspected for blisters, tears, or fish mouths
15 | Damaged areas repaired with patches extending minimum 150 mm past defect
16 | QA/QC inspection completed and signed off prior to backfilling
Code/Standard References:
• NBC Part 9 & 5 – Foundation Damp-Proofing & Waterproofing
• CSA A123.3, CAN/CGSB-37.58 – Sheet Applied Membrane Systems
• Manufacturer Specifications (e.g., Blueskin, Bituthene, Tremco, Soprema)
• Geotechnical / Civil Consultant Requirements