## Glazed Entrances QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification
1 | Door system type (swinging, sliding, automatic) matches approved shop drawings and schedules
2 | Frames, operators, safety sensors, hardware, thresholds match submittals
3 | Glazing type and thickness confirmed per code (tempered/laminated safety glass)
4 | Finish and color of system components match architectural specs
B. Frame and Opening Prep
5 | Opening framed level, plumb, and square with sufficient embed/support for frame anchoring
6 | Anchor embeds, blocking, wiring rough-ins installed prior to system arrival
C. System Assembly & Door Leaf
7 | Frame installed square, all perimeter sealed and shimmed
8 | Door leaves aligned, operated manually before power-up
9 | Panic hardware or locking mechanism functional and secure
10 | Glazing installed without scratches, edge damage, or misalignment
D. Operator & Power Activation
11 | Power wiring routed to operator and verified for voltage match
12 | Motion sensors and safety presence sensors installed and tested
13 | Push button (ADA) and activation zones tested with timed delay
14 | Door closes securely and reopens on obstruction during test
E. Accessibility, Life Safety & Code
15 | Clear opening width ≥ 850 mm (per NBC/ADA)
16 | Door swing or motion does not encroach on required path of travel
17 | All hardware reachable between 34–48" above finished floor
F. QA/QC Final Review
18 | System tested for full operation in power and manual mode
19 | Manufacturer commissioning and start-up log completed
20 | Consultant and envelope inspection (if applicable) signed off
Code/Standard References:
• NBC Part 3 & 9, CSA B651 / ADA – Accessibility
• ANSI/BHMA A156.10 / A156.19 – Automatic Door Systems
• CAN/CGSB 82.1, ULC S104 / ULC S106 – Glazing & Doors
• Manufacturer Specs: Kawneer, Horton, Dorma, Stanley, Besam