## Grease Interceptor QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittals & Pre-Installation
1 | Interceptor/separator type, size, and capacity match mechanical schedules and local bylaw requirements
2 | Manufacturer’s submittals stamped and reviewed; flow rate and retention volume confirmed
3 | AHJ (e.g., city plumbing inspector) notified if pre-installation approval required
B. Installation Checks
4 | Concrete pad/support base level and sized to hold interceptor weight (if not slab-on-grade)
5 | Pipe inlet/outlet slopes meet design (1–2%) and piping connected with flexible couplings or expansion joints
6 | Cleanout installed on both sides of the tank for maintenance
7 | Venting system connected to interceptor per manufacturer and local plumbing code
8 | External sensors (if specified) for high-level or oil detection connected and tested
9 | Signage or labelling provided above access covers or service ports
C. Testing & Commissioning
10 | System filled with water and observed for leaks or settlement before backfilling or concealment
11 | Functional test completed: verify no bypass of interceptor; float/oil skimmer devices tested
12 | Maintenance access clearance verified per local municipal code or design drawings
13 | Initial cleaning scheduled prior to occupancy or system turnover
D. Closeout
14 | Operation manual, maintenance logbook, and manufacturer warranty submitted
15 | Owner trained on cleaning schedule, maintenance frequency, and disposal records
16 | Commissioning and inspection forms signed off by AHJ
Code/Standard References:
• National Plumbing Code (NPC Canada), CSA B481 Series (Grease Interceptors)
• Local Municipal Bylaws (e.g., City of Calgary Sewer Bylaw 14M2012)
• Manufacturer Specs: MIFAB, Schier, Zurn, Highland, Canplas, Rockford Separators