## Gypsum Board QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification
1 | Gypsum type (regular, Type X, mold-resistant, tile backer) matches location and submittals
2 | Stud spacing, type, and gauge confirmed prior to boarding
3 | Fasteners, corner beads, trims, and backing materials match approved schedule/spec
B. Framing Inspection (Prior to Boarding)
4 | Wall framing inspected for plumb, alignment, and proper backing at openings and fixtures
5 | Inspections (electrical, plumbing, firestopping) signed off before boarding
6 | Fire/sound insulation and sealants installed prior to drywall closure
C. Board Installation
7 | Boards installed with staggered vertical joints; horizontal joints centered on framing
8 | Screws spaced correctly (typically 12" o.c. field / 8" o.c. edge unless otherwise specified)
9 | No overdriven screws, excessive gaps, or damaged boards
10 | Acoustic sealant applied at top/bottom plates and control joints (where required)
D. Finishing / Taping
11 | All joints taped and finished to specified level (e.g., Level 4 or 5 finish)
12 | Control joints, corner beads, and reveals installed straight and clean
13 | Compound sanding free from ridges, gouges, or scratches
E. Specialty Assemblies
14 | Shaft wall, fire-rated walls, chase walls completed to UL/WH assembly details
15 | Moisture-resistant boards used in wet areas per spec
16 | Lead-lined, acoustic, or impact-resistant boards verified where required
F. QA/QC & Final Punch
17 | Walls and ceilings visually inspected for level/plumb and uniformity
18 | Closeout documents submitted (UL assembly IDs, mock-up approvals if required)
19 | Surface ready for paint or finish without defects
Code/Standard References:
• NBC Part 9, ASTM C840 / C1396, GA-216 / GA-214 – Gypsum Board
• UL Design Assemblies, WHI, CGC, CertainTeed, National Gypsum Specs
• LEED / Acoustic Rating / Firestop Inspection Guidelines