## ITP - Division 03 Concrete
# | Activity / Description | Inspection Type | Responsibility | Acceptance Criteria / Standard | Records Required | QC Signoff | QA Signoff
1 | Formwork setup inspection | Hold Point | Contractor / QA/QC | CSA A23.1 / Approved drawings | Inspection report, photos
2 | Reinforcement layout and fixing | Hold Point | Contractor / QA/QC | CSA A23.3 / ACI 318 / Bar bending schedule | Rebar check report, photos
3 | Pre-pour review / access & readiness | Witness Point | QA/QC / Consultant | Site readiness checklist | Pre-pour sign-off sheet
4 | Concrete delivery ticket check | Surveillance | QA/QC | CSA A23.1 / Delivery documentation | Delivery tickets
5 | Slump, temperature, air content test | Inspection | QA/QC / 3rd Party | CSA A23.2 | Concrete test report
6 | Concrete pouring and vibration | Surveillance | QA/QC | ACI 309 | Daily pour log
7 | Placement technique and finish monitoring | Surveillance | QA/QC | ACI 301 / Project specs | Photos, pour checklist
8 | Specimen collection for compressive testing | Inspection | QA/QC / Testing Lab | CSA A23.2 | Sample log, test results
9 | Curing method and timing verification | Inspection | Contractor / QA/QC | CSA A23.1 / ACI 308R | Curing log, photos
10 | Form stripping (beams, slabs, columns) | Witness Point | QA/QC / Engineer | ACI 347.3R / Project schedule | Strip log
11 | Surface defects and honeycombing check | Inspection | QA/QC | Project specs / tolerances | Punch list, repair record
12 | Grouting of precast joints and embeds | Hold Point | Contractor / QA/QC | CSA A23.4 / Product specs | Grouting checklist
13 | Final QA sign-off and turnover for next trade | Inspection | QA/QC | Project QA requirements | QA sign-off form