## Lighting Controls QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittals & Controls Review
1 | Approved control narrative, zoning diagrams, and fixture schedules reviewed
2 | Sensor types and locations (ceiling, wall, dual-tech) coordinated and shown on drawings
3 | Daylight zones defined and photocells located per design and LEED intent (if applicable)
B. Device Installation
4 | Sensors and switches installed at correct height, orientation, and range adjusted
5 | All wall stations, keypads, dimmers, and override switches installed cleanly and labeled
6 | Low-voltage wiring terminated, tagged, and run in dedicated conduits
7 | Panelboard relays and lighting controllers mounted in labeled, accessible locations
C. Integration & Programming
8 | Lighting control system networked with BAS (if required) and IP address mapped
9 | Dimming and switching logic programmed as per room functions
10 | Daylight harvesting, occupancy timeout, and override settings uploaded and tested
D. Testing & Commissioning
11 | Zone-by-zone test for sensor response, dimming control, and relay behavior
12 | Emergency lighting override tested and functional
13 | Lighting schedules (weekday/weekend/holiday) uploaded and validated
14 | Graphics interface (if applicable) reviewed with client
E. Closeout
15 | Final commissioning report, zone maps, and user override instructions submitted
16 | Operator training complete and system login credentials handed off
Code/Standard References:
• ASHRAE 90.1, NECB Lighting Controls, IECC Section C405, CSA C22.1
• LEED v4 Lighting Credit
• Manufacturer Specs: Lutron, Crestron, Leviton, Acuity, nLight, Encelium