## Low-Slope Roofing QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification & Storage
1 | Roofing membrane type (TPO, SBS, EPDM, etc.) as per approved submittal
2 | Insulation type, R-value, and overlay board per drawing and CAN/ULC-S704 standard
3 | Adhesives, sealants, cleaners, fasteners, and flashings per manufacturer recommendation
4 | All materials protected from UV, rain, and stored dry on pallets/sleepers
B. Pre-Installation Coordination
5 | Pre-installation meeting conducted with roofing sub, consultant, and owner
6 | Wind uplift calculations performed using NRC Wind-RCI tool and approved design submitted
7 | All penetrations, vent stacks, drains, parapets prepared before install
C. Substrate & Vapor Retarder Prep
8 | Substrate dry, clean, firm, and approved by consultant
9 | Vapor retarder membrane installed continuous with sealed laps and terminations
10 | Nailers installed per detail and fastened with 300 kg/m resistance capacity
D. Insulation & Overlay Board
11 | Insulation boards staggered and tight, no gaps; damaged boards replaced
12 | Overlay board installed using full bead adhesive per manufacturer’s spacing and coverage
E. Membrane Installation
13 | TPO/EPDM/SBS membrane installed straight with minimum overlap (typically 75–150 mm)
14 | Membrane fastened per uplift specs; no overdriven fasteners
15 | Field seams welded by trained operator using automatic hot-air welder; hand welds only for repairs
16 | Exposed membrane cleaned with TPO Weathered Cleaner if >7 days old before welding
F. Flashing & Penetrations
17 | Base and curb flashings installed continuous, reinforced per spec
18 | Drain pans, pipe boots, stack covers installed and welded/sealed correctly
19 | Edge metal, termination bars, and sealants installed and approved
G. Final Review & QA
20 | QA/QC and third-party inspection conducted prior to warranty request
21 | Walkway protection boards installed around rooftop units
22 | Roofing warranty issued (10-year minimum full system) covering membrane and workmanship
Code/Standard References:
• NBC Part 5 & 9 – Roofing Systems
• CSA A123.21 / ULC-S704 / ULC-S107 – Membrane and Roofing Systems
• Manufacturer Specs: Firestone, Soprema, Carlisle, Lexcan, etc.
• ARCA Roofing Standards Manual, Wind-RCI Tool, LEED/Energy Star (if applicable)