## Masonry QAQC Checklist
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification
1 | Masonry units (CMU/brick) as per approved submittals and specification
2 | Units stored properly on level ground, protected from moisture
3 | Mortar type and mix confirmed per specification
4 | Reinforcement and ties (ladders, dowels, bars) per approved drawings
B. Wall Layout and Setup
5 | Layout verified per architectural and structural plans
6 | First course set true, plumb, and level
7 | Control and expansion joints located and detailed correctly
8 | Weep holes and flashing installed at appropriate intervals
C. Masonry Execution
9 | Bonding pattern consistent and as per drawings
10 | Joint thickness uniform and as per tolerance (typically 3/8”)
11 | Reinforcement placed correctly in cores, tied, and inspected prior to grouting
12 | Grout mix, placement, and consolidation as per standard
13 | Tooling of joints (concave, flush) per specification
D. Cleaning and Protection
14 | Wall cleaned using approved methods without staining or damage
15 | Work area protected from weather (cold/hot) during and after installation
16 | Masonry protected from construction damage (rebar, rework, patching)
17 | Final inspection completed and ready for following trade
Code/Standard References:
• CSA A371 – Masonry Construction for Buildings
• CSA A179 – Mortar and Grout for Unit Masonry
• NBC Part 9 and 4 – Masonry Construction
• Project Specifications and Drawings