## Metal Decking QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification
1 | Decking type, gauge, and profile match approved shop drawings and submittals
2 | Deck panels free from damage (dents, corrosion, deformation)
3 | Deck panels stored on level supports and protected from weather
B. Installation – General
4 | Decking installed with ribs facing the correct direction and aligned per drawings
5 | Deck laps and end joints have minimum specified overlap (typically 2”)
6 | Sheets are tightly butted, without gaps or misalignments
C. Fastening and Anchorage
7 | Welded deck: Welds are full and continuous at supports and side laps
8 | Screwed deck: Screws driven as per manufacturer spacing/layout
9 | Anchorage to structural steel verified with approved fastener/weld detail
10 | Edge closures, pour stops, and angle supports properly installed and secured
D. Openings and Penetrations
11 | Openings cut only after layout verification and coordination with trades
12 | Reinforcement or edge framing installed around large openings
E. Safety and Final Review
13 | Temporary bracing and safety measures (fall protection) in place
14 | QA/QC inspection and consultant sign-off before concrete or roofing installation
Code/Standard References:
• CSA S136 – Cold-Formed Steel Structural Members
• SDI (Steel Deck Institute) Standards – Installation, Design, Welding
• Project Specifications and Drawings
• NBC Part 4 – Structural Framing Requirements