## PEMB QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittals & Pre-Delivery Review
1 | Shop drawings and structural design reviewed and approved
2 | Anchor bolt plans issued and coordinated with foundation design
3 | Certified engineered drawings (stamped) submitted and match building permit set
4 | Delivery checklist confirmed: main frames, girts, purlins, panels, accessories, fasteners
B. Foundation and Anchor Bolt Prep
5 | Anchor bolts installed per layout, elevations, and embedment requirements
6 | Bolt threads clean, protected, and plumb prior to structural steel arrival
7 | Concrete flatness, level, and hold-down locations verified
C. Frame Erection
8 | Structural steel members inspected for damage, twist, corrosion
9 | Frames erected plumb and braced per sequence in erection manual
10 | Bolts torqued and documented per manufacturer's tensioning specs
11 | Temporary bracing in place during all phases of erection until diaphragm secured
D. Roof and Wall Panel Installation
12 | Insulation, vapor barrier, and liner panels (if used) installed as per system
13 | Panels installed straight, with correct lap orientation and spacing
14 | Fasteners spaced per drawing and properly seated (not overdriven/underdriven)
15 | Flashing, trim, sealant, and closures installed without gaps or buckling
E. Final Inspection & Closeout
16 | Downspouts, gutters, ridge vents, and louvers installed complete
17 | Punch list items (panel scratches, open seams, missing hardware) corrected
18 | Warranty documents, erection certificate, and O&M manuals submitted
19 | Structural engineer and manufacturer signoff received (if required)
Code/Standard References:
• CSA A660, NBC, MBMA Manual, CAN/CSA S16, AISC, ASTM A325/A490
• Manufacturer Specs: Butler, Varco Pruden, Star, Robertson, Metallic, Nucor, Behlen