## Polished Concrete QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material & Slab Verification
1 | Concrete slab meets minimum compressive strength (typically ≥ 3000 psi)
2 | Mix design reviewed for compatibility with polishing system (low air, minimal SCMs)
3 | Slab poured flat with minimal crown/camber (FF/FL targets if specified)
4 | No curing compounds or surface sealers used unless approved for polishing
B. Pre-Grind Preparation
5 | Protection from early trades removed; surface cleaned of glue, coatings, or debris
6 | Cracks and divots patched with compatible filler prior to grinding
7 | Areas with embedded items or poor coverage identified and masked (if needed)
C. Grinding & Densifying
8 | Initial metal bond grinding completed per manufacturer’s step sequence
9 | Joints and cracks filled and flush post-initial grind
10 | Densifier applied and allowed to penetrate per manufacturer’s dwell time
11 | Intermediate and fine diamond polishing passes completed in sequence
D. Finish & Protection
12 | Polished to specified gloss level (typically 400 / 800 / 1500 / 3000 grit)
13 | Guard/sealer (if used) applied evenly with no streaks
14 | Edges and corners polished to match field finish
15 | Traffic protection measures applied after polishing (mats, warnings)
E. Final Review
16 | Reflectivity and clarity visually confirmed
17 | No swirl marks, haze, or inconsistent polish across zones
18 | Gloss meter readings (if required) documented
19 | Consultant and owner signoff received
Code/Standard References:
• ACI 310R, ASTM E430, C150, ASTM C1028, NFPA 101
• Concrete Polishing Council (CPC) Standards
• Manufacturer Specs: RetroPlate, Ashford Formula, Prosoco, Ameripolish, Laticrete