## Resilient Flooring QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification
1 | Flooring type (LVT, VCT, sheet vinyl, rubber) and pattern match finish schedule and approved submittals
2 | Adhesive, moisture barrier, and levelling compound match manufacturer’s system
3 | Baseboards, nosings, reducer strips, and accessories confirmed on site
4 | Materials stored flat, clean, and conditioned for 24–48 hrs per manufacturer
B. Substrate Preparation
5 | Subfloor dry, flat, smooth, and cleaned of dust or debris
6 | Floor levelled to spec (typically ≤1/8” in 10 feet)
7 | Moisture content and RH tested and within limits for flooring system
C. Layout & Installation
8 | Layout approved and aligned with architectural drawing or reference point
9 | Directional arrows followed (if LVT or rubber planks)
10 | Adhesive applied uniformly, allowed open time, and flooring rolled as per spec
11 | Expansion joints installed at required locations and door thresholds
12 | No bubbles, curling, or hollow spots in finished surface
D. Finish Trims & Accessories
13 | Cove base or straight base installed cleanly and tight to wall
14 | Transition strips secure and smooth at doorways or flooring changes
15 | Stairs: nosings, treads, and risers properly aligned and glued
E. Final Inspection & Punch
16 | Surface clean and free from residue, adhesive stains, or scuff marks
17 | Visual inspection completed by contractor and consultant
18 | Closeout documents submitted (warranties, cleaning instructions, adhesives used)
Code/Standard References:
• ASTM F710, ASTM F1869, ASTM F2170 – Substrate Conditions
• NBC, LEED VOC Compliance
• Manufacturer Specs: Tarkett, Armstrong, Forbo, Mondo, Mannington, Gerflor