## Site Furnishings QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittals & Layout Verification
1 | Shop drawings and cutsheets reviewed for each furnishing item (bench, bike rack, bollard, receptacle, etc.)
2 | Furnishing layout coordinated with civil/landscape drawings and staked
3 | Conflicts with sidewalks, trees, hydrants, utilities, and clearances resolved before install
B. Foundation and Surface Prep
4 | Concrete pad or base slab complete and verified flat and level
5 | Anchor bolts, sleeve inserts, or embedded plates located and coordinated
C. Installation of Furnishings
6 | Bench alignment consistent with drawings and parallel to curb/sidewalk
7 | All anchor bolts torqued and hidden hardware capped (if applicable)
8 | Bollards installed at correct spacing, depth, and setback (e.g., min 1m clearance)
9 | Waste/recycle receptacles mounted plumb, accessible, and with liners installed
10 | Bike racks anchored securely and accessible with no conflict with pedestrian paths
D. Final Inspection & Acceptance
11 | All site furnishings cleaned, tags removed, and inspected for damage
12 | All furnishings meet accessibility standards for height, spacing, and placement
13 | Final layout confirmed by consultant or landscape architect
Code/Standard References:
• CSA Z614, ASTM F3012, Municipal Streetscape Guidelines, CPTED Principles