## Stairs & Handrails QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification
1 | Stairs and handrails match approved shop drawings and specifications
2 | All components properly labeled for assembly (stringers, treads, landings, railings)
3 | Surface finish verified (galvanized, primed, powder-coated, stainless, etc.)
B. Fabrication and Fit-Up
4 | Stringers fabricated to correct rise/run and dimensions
5 | Tread and riser spacing consistent and within building code tolerance
6 | Welds continuous and smooth; cut edges deburred
7 | Platforms/landings square and level
C. Installation
8 | Units installed at correct elevation and orientation per drawings
9 | Anchors and supports correctly sized, torqued, and embedded
10 | Handrail height, spacing, and returns per code and shop drawings
11 | Guardrails and pickets installed securely and meet code spacing (e.g., < 4")
D. Safety & Finishing
12 | Anti-slip nosing or coating applied to treads
13 | Exposed ends ground smooth; no sharp projections
14 | Site coating touch-ups completed after welds/handling
15 | Final inspection approved by QA/QC and safety officer
Code/Standard References:
• NBC Part 3 and 9 – Stair and Guard Requirements
• CSA S157 / CSA W59 – Steel Connections and Welding
• CISC Design Guide – Stair Systems
• Project Specs & Architectural Details