## Thermal Break QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification
1 | Thermal break materials (insulating pads, blocks, composite shims, structural insulation) per submittals
2 | System manufacturer and load ratings match structural/architectural specs
3 | Product certification or test data provided (e.g., thermal resistance, compressive strength)
B. Substrate & Interface Prep
4 | Substrates (steel, concrete, aluminum) clean and prepared as per manufacturer's instructions
5 | All mating components dimensionally checked for flatness and fit prior to install
C. Installation – Curtain Wall / Window Systems
6 | Thermal breaks in aluminum mullions installed continuously without gaps
7 | Insulating strips snapped or bonded into frame with proper compression
8 | Frames and sills sealed to adjacent air/vapor barrier without thermal bridging
D. Installation – Steel Support & Connection Plates
9 | Thermal isolator plates or bushings installed between cladding supports and structure
10 | Insulating washers or sleeves used on through-bolts as required
11 | No direct metal-to-metal contact between cladding fasteners and building frame
E. Installation – Balconies & Slab Edges (Thermal Inserts)
12 | Thermal isolation elements placed per structural drawings at balcony/slab interfaces
13 | Rebar connections pass through insulation with proper cover and spacing maintained
14 | Joint treatment between slab and facade integrates with WRB/vapor barrier
F. Final QA Review & Documentation
15 | All thermal break assemblies verified against shop drawings and manufacturer install guides
16 | QA/QC and building envelope consultant sign-off completed before enclosing facade
17 | Thermal break components labeled or tagged for traceability (if required by spec)
Code/Standard References:
• NECB 2020, NBC Part 5 & 9 – Thermal Bridging and Envelope
• CSA A440.6 / ASTM C1363 / ISO 10211 – Thermal Transmittance Testing
• Manufacturer Specs: Schöck, Armatherm, Isokorb, Technoform
• LEED / Passive House / Envelope Commissioning Requirements