## Vapor Retarder QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification
1 | Vapor retarder type and perm rating confirmed (e.g., ≤0.1 perm for Class I)
2 | Product listed on approved submittals and compatible with adjacent materials
3 | Sealants, tapes, and primers used are approved and compatible
4 | Materials stored dry and undamaged prior to install
B. Substrate Preparation
5 | Substrate dry, clean, and smooth (no protrusions, moisture, or contaminants)
6 | All penetrations pre-coordinated with trades
C. Wall Application (Interior/Exterior)
7 | Continuous installation without tears or holes
8 | Seams overlapped (minimum 100 mm / 4”) and sealed with approved tape
9 | Membrane turned up at floor slab and down over top plates / headers
10 | Penetrations sealed with gaskets, boots, or tapes (MEP, structural)
11 | Backed up with rigid board, batt insulation, or sheathing as per design
D. Under-Slab Vapor Barrier (if applicable)
12 | Sheet lapped a minimum of 150 mm (6”) and sealed
13 | Penetrations (conduits, footings) sealed individually
14 | No punctures or wrinkles under reinforcement or rebar
15 | Vapor barrier extended under footings or up vertical face (as per detail)
E. Roof Application (TPO/SBS Hybrid)
16 | Vapor retarder installed over deck and under insulation as per spec
17 | Torch or self-adhered membrane sealed at all laps and terminations
18 | Mechanical fasteners used only where permitted by manufacturer
F. Final Review & Coordination
19 | QA/QC inspection with air barrier continuity check
20 | Any repairs completed with full bond and continuity re-established
Code/Standard References:
• NBC Part 5 – Vapour Diffusion Control
• CAN/CGSB 51.33, ASTM E96 – Vapor Retarder Classifications
• NECB / Energy Codes
• Manufacturer Specifications (e.g., Stego Wrap, Soprema, Henry, Blueskin)
• Air/Vapor Barrier Continuity Testing Guidelines (if applicable)