## Wall Coverings QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material Verification
1 | Wall covering type (vinyl, fabric, wood, FRP) and pattern matches finish schedule
2 | Adhesive type and spread rate match approved submittals and manufacturer guidance
3 | Accessory trims (corner guards, base reveals, end caps) reviewed and on site
4 | Rolls or panels conditioned and inspected for dye lot or surface flaws
B. Surface Preparation
5 | Substrate clean, smooth, and sealed if required (especially drywall)
6 | Primer or sizing applied to porous or gypsum surfaces per spec
7 | Wall surface flat and free from bumps or defects visible through covering
C. Installation – Sheet Vinyl or Fabric
8 | Pattern alignment verified at seams and corners
9 | Seams tight and not overlapped unless manufacturer allows
10 | Corners tight and top edge aligned with control or datum line
D. Installation – FRP or Wood Panel Systems
11 | Panels cut cleanly, fit tight to corner trims, and gapped per spec
12 | Adhesive coverage >95% with consistent contact on substrate
13 | Mechanical fasteners installed per detail (if required)
E. Finishing & Cleanup
14 | All exposed trims and accessories installed straight and flush
15 | Surface cleaned, no glue bleed, bubbles, or discoloration
16 | Final walkthrough approved by consultant and punchlist cleared
Code/Standard References:
• ASTM F793 / F742, ASTM E84 – Wall Covering Fire and Physical Standards
• LEED VOC Compliance, NFPA 101
• Manufacturer Specs: Koroseal, Maharam, MDC, Marlite, Crane Composites