## Window Treatments QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Material & Submittals Review
1 | Shade/blind type, color, and openness factor matches submittals and finish schedule
2 | Control type (manual chain, clutch, motorized) matches drawings and client requirement
3 | Drapery track material, color, and pleat type confirmed (for curtains)
4 | Safety compliance documents (e.g., chain tensioners, child-safety devices) included
B. Rough Opening Coordination
5 | Mounting type (inside jamb, surface, ceiling recessed) coordinated with ceiling/wall finish
6 | Power rough-in location coordinated and voltage confirmed for motorized units
7 | Any light gap mitigation requirements confirmed with architect/interior designer
C. Installation Checks
8 | Mounting brackets securely fastened to blocking or substrate
9 | Shades/blinds level, aligned, and operate smoothly
10 | Chain tensioners or wand controls installed as per manufacturer specs
11 | Drapery moves smoothly on track, overlaps correctly, and returns properly
D. Motorized Systems (if applicable)
12 | Motor powered and controlled by wall switch, remote, or integrated control system
13 | Programming complete for grouped, preset, or scene control
14 | Wireless/Bluetooth/Zigbee compatibility confirmed (if required)
E. Final Review
15 | Shades/drapery free from creases, damage, misalignment
16 | Closeout package submitted: warranties, operation manual, maintenance care
17 | Client/consultant signoff completed
Code/Standard References:
• NBC, ANSI/WCMA A100.1, LEED EQ Credit: Daylight & Views
• Manufacturer Specs: Hunter Douglas, Lutron, Mecho, Draper, Silent Gliss, Graber, Somfy