## Wiring Devices QAQC
# | Inspection Item | Pass | Fail | N/A | Comments / Notes
A. Submittals & Layout Verification
1 | Approved wiring device schedule reviewed and matched to architectural layout
2 | Device types (decora, tamper-resistant, GFCI, USB, dimmer) coordinated with spec and finishes
3 | Height and spacing checked against accessibility standards and project specs
B. Rough-in Inspection
4 | Box sizes adequate for conductor fill and mounting
5 | Conductors terminated properly with no exposed copper
6 | GND conductors bonded to box (if metal) and device grounding terminal
7 | AFCI/GFCI circuits connected to correct line/load terminals and identified properly
C. Trim-out Inspection
8 | Devices securely mounted flush to wall finish (GWB, tile, concrete, wood)
9 | Cover plates flush, aligned, undamaged, and color-matched
10 | GFCI receptacles tested for trip and reset functions
11 | Dimmer switches and multi-way switches tested for function
12 | USB outlets powered and tested with load
D. Final Testing & Closeout
13 | All receptacles voltage-tested for polarity and grounding
14 | Device labeling complete (breaker ID, circuit ref) where applicable
15 | As-built location drawings and inspection logs submitted
Code/Standard References:
• CSA C22.1 (CEC Section 26, 86), NEC Article 210 & 406, UL 498, CSA B651
• Manufacturer Specs: Leviton, Lutron, Hubbell, Eaton, Pass & Seymour, Schneider Electric